## Sheet1
Potholes Logged with Devon County Council |  |  | https://www.devon.gov.uk/roadsandtransport/report-a-problem/report-a-pothole/
No. | Date Reported | Location | Reported By | Reported To | Logged By | Log Date | Ref | Assessment by | Planned completion | Completion | What3Words | Tarmac Containers Used | Comments
1 | 2023-06-02 | Rudge Hill | Wendy Chapman | Lis Wallace | James Cater | 2023-06-04 | W231633796 | 2023-06-11 | 2023-09-17 | 2023-06-23 |  |  | Mouth of junction at Rudge Cross
2 | Unknown | Rudge Hill | Unknown | n/a | Unknown | 2023-05-23 | W231630451 | 2023-05-30 | 2023-06-22 | 2023-06-12 |  |  | Near Rockvale.
3 | 2023-06-03 | Rudge Hill | James Cater | n/a | James Cater | 2023-06-04 | W231633799 | 2023-06-11 | 2023-09-17 | 2023-06-22 |  |  | Near man hole cover at Lustleigh sign
4 | 2023-06-05 | A382 | James Cater | n/a | James Cater | 2023-06-05 | W231634207 | 2023-06-08 | 2023-09-17 | 2023-06-21 |  |  | A328 south of Plumley junction
5 | 2023-06-20 | Knowle Road/Yonder Wreyland | Jeremy Grammer | n/a | Jeremy Grammer | 2023-06-20 | W231639721 | 2023-06-27 | 2023-06-21 | 2023-06-20
6
7 | 2023-07-08 | Opposite telephone exchange | Jeremy Grammer | n/a | Jeremy Grammer | 2023-07-08 | W231644595 | 2023-07-15
8
9 | [9 empty] | 2023-02-09 | counters.stocked.swarm | 6 | R.Clark, A.Beare, A.Hockings, M. Strudley
10 | [9 empty] | 2023-02-09 | fuzzy.claw.thigh | 1.5 | R.Clark, A.Beare, A.Hockings, M. Strudley
11 | [9 empty] | 2023-02-09 | wisdom.cools.video | 2 | R.Clark, A.Beare, A.Hockings, M. Strudley
12 | [9 empty] | 2023-02-09 | soulful.nicknames.documents | 2.5 | R.Clark, A.Beare, A.Hockings, M. Strudley
13 | [9 empty] | 2023-02-09 | essay.eternally.wriggled | 0.5 | R.Clark, A.Beare, A.Hockings, M. Strudley
14 | [9 empty] | 2023-02-09 | pools.icebergs.librarian | 2.5 | R.Clark, A.Beare, A.Hockings, M. Strudley
15 | [9 empty] | 2023-02-23 | roofs.shins.should | 11 | A.Beare, A.Hockings, M. Strudley, G Stone
16 | [9 empty] | 2023-02-23 | spicy.flattens.fallen | 1 | A.Beare, A.Hockings, M. Strudley, G Stone
17 | [9 empty] | 2023-06-14 | strapping.popping.price | 7 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
18 | [9 empty] | 2023-06-14 | season.rationed.neatly | 4 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
19 | [9 empty] | 2023-06-14 | starting.swerving.jogging | 1 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
20 | [9 empty] | 2023-06-14 | assembles.requiring.teeth | 1 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
21 | [9 empty] | 2023-06-14 | stroke.condense.forensic | 2 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
22 | [9 empty] | 2023-06-14 | stroke.condense.forensic | 2 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
23 | [9 empty] | 2023-06-14 | torches.cape.mailboxes | 1 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
24 | [9 empty] | 2023-06-14 | torches.cape.mailboxes | 1 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
25 | [9 empty] | 2023-06-14 | torches.cape.mailboxes | 1 | A.Beare, A.Hockings, M. Strudley,R. Clark, J. P-Tuck
26
[8 empty] | Key: |  | Assessed, Agfreed and Passed to Contractor
Potholes planned to be addressed by the Lustleigh Pothole Team; | [9 empty] | Completed
1 | Knowle Road from A382 to Brookfield (including private road pothole & pothole on road to Loxtor) – All potholes will be filled, including those reported by JG and Tim.
2 | Rudge Cross – 2 very large holes (95cmx40cmx80mm depth &102cmx90cmx 72mm depth) and 2 smaller potholes.
3 | Mapstone – 5 potholes (30-50cmx20-30cmx 50-70mmdepth)
4 | Ellimore farm road – several potholes
5 | Road Ellimore to Pethybridge 6 potholes
6 | Road Sanduck to Narramore 8 potholes
7 | Main route into Lustleigh fromA382 – 1 large pothole
8 | Rudge Hill – 1 large pothole
9
10